NYISO Stochastic UC Pipeline

14-Month Project Timeline

Valentin — Princeton ORFE

# 1. Purpose of this document

This document inventories every subtask across Tasks 1.1 through 2.2, assesses current status honestly against what has actually been built and validated, and builds a 14-month timeline that orders work by dependency rather than by task number.

The goal is a pipeline that is trustworthy across multiple years, publishes at least one research result mid-timeline, and completes all project deliverables including the AGILe Digital Twin integration by the end of the project horizon.

Two conventions apply throughout. First, "done" means validated and trustworthy — mechanism alone is not enough. Second, the timeline is ordered by technical dependency, not by task number; Task 1.5 items appear as early as Month 3 where they unblock downstream work.

## Status legend

| DONE | Validated and trustworthy. Covered by tests or clear evidence. |
| --- | --- |
| PARTIAL | Mechanism exists but meaningful coverage or calibration is missing. |
| NOT STARTED | No work yet in this area. |

# 2. Full subtask inventory

Every bullet point in Tasks 1.1 through 2.2, with current status and notes. This inventory is the input to the timeline; reading it is the best way to understand why the schedule is ordered the way it is.

One clarification on the "software architecture" subtask in Task 1.2: the module wiring between PGscen and Vatic (NyisoLoader, dispatcher, data flow) is trustworthy, but the electricity grid representation inside that architecture carries debt that affects research credibility. Kron reduction fidelity, topology refresh for post-2019 infrastructure, per-bus LMP validation, and several calibration items are still open. That work appears across Months 1-6 of the timeline; collectively it is what finishes the "software architecture" subtask in the broader sense.

| Task | Subtask | Status | Notes |
| --- | --- | --- | --- |
| 1.1 | Build data structures for weather and wind/solar historical data | PARTIAL | PGscen-NYISO metadata complete (31 wind + 16 solar plants with lat/lon). HRRR pipeline exists but not systematic across all years. Grid-scale solar limited to 2 sites in 2019. |
| 1.1 | BESS added to Vatic software module | DONE | Blenheim-Gilboa and Lewiston wired. SOC persistence bug caught and fixed. Synthetic BESS test pattern established. Regression tests in place. |
| 1.2 | Identify data sources and develop data integration plan | DONE | NYISO_DATA_SOURCES.md catalogues MIS, Gold Book, EIA endpoints. |
| 1.2 | Define software architecture for PGScen and Vatic integration | PARTIAL | Module wiring done: NyisoLoader produces template + timeseries, registered in load_input dispatcher. But the grid model itself is not fully validated: Kron reduction never cross-checked against full NPCC-140; topology frozen at 2019 (no CHPE, Clean Path NY, Smart Path); external import pricing limited (Path B not implemented); zonal reserves absent; per-bus LMPs never validated; heat rates frozen. Module architecture is trustworthy; grid representation inside it carries debt. |
| 1.2 | Develop code for data integration | PARTIAL | Thermal FleetUpdater works. BESS fleet updater does not exist. Batteries beyond pumped storage not auto-populated. |
| 1.2 | Build databases for PGScen and Vatic | PARTIAL | File hierarchy under data/nyiso_cache/. No schema, index, or provenance tracking. Needs to become a queryable database. |
| 1.2 | Define NYCA inter-area flow | PARTIAL | 7 internal interfaces calibrated. 4 external equivalents exist but known-limited (import cost/Pmax coupling). No standalone methodology document. |
| 1.2 | Develop code to generate Monte Carlo scenarios | PARTIAL | PGscen generates load/wind/solar scenarios via GEMINI. Generator outages and transmission contingencies not modeled. |
| 1.2 | Use Monte Carlo engine to create a historical database | NOT STARTED | One ensemble run for July 2019. No systematic archive of ensemble results across years. |
| 1.3 | Develop data integration plan | DONE | Covered by 1.2 plan at document level. |
| 1.3 | Develop code for weather data integration | PARTIAL | HRRR ingestion exists in PGscen-2nd. Not all years systematically covered. No unified get_nyiso_weather(year) interface. |
| 1.3 | Develop code to generate grid-scale wind and solar | PARTIAL | Wind works (31 plants). Solar has only 2 sites in 2019. Growth for 2020+ not integrated into FleetUpdater. |
| 1.3 | Develop code to integrate behind-the-meter solar | NOT STARTED | ~6 GW of NY distributed solar currently absorbed in net load. No explicit BTM model. |
| 1.3 | Develop and execute a test plan | PARTIAL | 21 fast + 2 slow regression tests, mutation tests. Cross-year validation done for 2020, 2022, 2023. No systematic test plan document. |
| 1.4 | Evaluate outputs against NYS Digital Twin | NOT STARTED | No interface with AGILe's Digital Twin yet. |
| 1.4 | Tests conducted for a selected NYISO class year | PARTIAL | July 2019 validated against NYISO. Digital Twin comparison is separate deliverable still pending. |
| 1.4 | Iterative testing until consistent with Digital Twin and NYISO DA outcomes | NOT STARTED | Gated on Digital Twin interface being built. |
| 1.5 | Integrate Market Emulator with AGILe's NYS Digital Twin | NOT STARTED | Core integration task for final phase. |
| 1.5 | Transfer hourly dispatch, storage, and bus-level load to Digital Twin | NOT STARTED | Output capability exists in Vatic. Formatting and transfer mechanism to build. |
| 1.5 | Detailed user instructions procedure | PARTIAL | PIPELINE_STATUS.md is a seed. Full user procedure for Market Emulator not written. |
| 1.5 | Final report including software documentation and demonstration | NOT STARTED | End-of-project deliverable. |
| 2.1 | Large-scale stochastic model for NYS grid from weather data | PARTIAL | PGscen-NYISO is the stochastic model. Current scale: 31 wind + 16 solar + 11 load zones. 'Large-scale' interpretation needs PI confirmation. |
| 2.1 | Code to simulate Monte Carlo scenarios from large-scale model | PARTIAL | Works at current scale. Needs to scale as stochastic model grows. |
| 2.2 | Tune optimal schedules for cost vs. environmental performance tradeoffs | NOT STARTED | Requires emissions accounting (RGGI, SO2, NOx, methane) added to objective or constraint. |

# 3. Cross-cutting issues

These are real work items surfaced during development that don't map cleanly to a single task bullet but need resolution. They are tracked separately so they don't get lost between tasks.

| Issue | Impact | Addressed in |
| --- | --- | --- |
| Import cost/Pmax coupling | Fixed-cost external equivalents distort 2022 LMPs when Pmax is raised. | Months 1-2 (Path B) |
| Zonal reserve requirements missing | SENY and NYC reserves not modeled. Understates downstate LMPs. | Months 3-4 or later |
| Kron reduction fidelity not cross-checked | Reduced network never validated against full NPCC-140. | Months 7-8 |
| Per-bus LMP validation never done | Only zonal averages compared to NYISO. Limits Task 1.4 credibility. | Months 3-4 |
| Heat rates frozen at 2019 | Affects all year-specific simulations. Small but systematic. | Months 1-2 (document) |
| IP2 mid-2020 retirement timing | September 2020 model overstates nuclear by ~1 GW. | Months 1-2 |
| BTM solar not modeled explicitly | Listed in Task 1.3. Connects to Task 2.1 scale. | Months 5-6 |
| Stochastic experiment under old calibration | July 2019 ensemble predates v1 calibration. Cannot be cited as-is. | Months 1-2 (pilot) |

# 4. Timeline at a glance

| Months | Focus | Tasks served | Key deliverables |
| --- | --- | --- | --- |
| 1-2 | Foundation lock-in | 1.1, 1.2 | v1-calibrated stochastic pilot, BESS real fleet updater, queryable database, calibration gaps closed, 6-year validation sweep. |
| 3-4 | Inter-area flow and Digital Twin interface | 1.2, 1.4, 1.5 | NYCA flow methodology doc, Digital Twin data schema, first Digital Twin comparison report. |
| 5-6 | Task 1.3 completion | 1.3 | Full-year HRRR pipeline, grid-scale solar integrated, BTM solar decision and implementation, test plan document. |
| 7-8 | First research experiment | 1.2, paper | Cross-year cost-of-uncertainty study, systematic MC historical database, first paper draft. |
| 9-11 | Task 2.1 | 2.1 | Large-scale stochastic model (scope set with PI), extended ensembles. |
| 12-13 | Task 2.2 | 2.2 | Emissions accounting, cost vs. environmental tradeoff curves. |
| 14 | Task 1.5 finalization | 1.5 | Digital Twin integration finalized, user procedure, final report. |

# 5. Detailed phases

## Months 1-2: Foundation lock-in

Goal: everything built so far becomes trustworthy and reproducible. No new research yet. Completes Task 1.1 at the ambitious interpretation and puts Task 1.2 on solid ground.

### Weeks 1-2: v1-calibrated stochastic pilot

Re-run the July 2019 stochastic experiment (100 scenarios, 7 days) under v1 calibration: mandatory warmup day, 2,620 MW fixed reserve, v1 import limits, BESS with SOC persistence. This is the sanity check that the integrated pipeline produces stable results end-to-end.

- Deliverable: report_v1.md with cost-of-uncertainty, LMP fan chart, commitment heatmap.

- Gate: >90 of 100 scenarios complete and LMPs plausible vs NYISO actuals.

- If gate fails, fix before moving on.

### Weeks 2-3: BESS fleet updater

Build nyiso_bess_updater.py parallel to the thermal FleetUpdater. Pull battery storage from Gold Book Section III-2 and NYISO interconnection queue. Auto-populate storage dict per year. Covers Ravenswood BESS (2023), East River, Long Island batteries.

- Replaces synthetic BESS test fixtures with real per-year inventory.

- Completes Task 1.1 BESS work in the ambitious interpretation (real fleet, not just mechanism).

- Keep synthetic BESS pattern available as a test tool.

### Weeks 3-4: Database layer

Move from file hierarchy to a real database (SQLite is sufficient) for cached NYISO and EIA data. Schema: tables for generators, interface flows, LMPs, fuel prices, all keyed by year and date. Add provenance columns.

- Satisfies Task 1.2 "Build databases for PGScen and Vatic" bullet.

- Benefits: queryable, versioned, auditable.

- Migration script from current file-hierarchy cache.

### Weeks 4-6: Close the three biggest modeling gaps

- Implement Path B for import pricing: year-specific import costs based on Zone D LMP trends. Resolves the cost/Pmax coupling known-limitation. Pre-requisite for Task 1.4 validation quality.

- Apply IP2 mid-2020 retirement override (model-level, not Gold Book level).

- Document heat rate methodology: explicit decision to leave frozen at 2019 with disclaimer, or update per year. Recommendation: leave frozen, document.

### Weeks 7-8: Multi-year cross-validation sweep

Run deterministic 3-day validations across 2019, 2020, 2021, 2022, 2023, 2024 on matched calendar weeks. Add 2021 (previously skipped) and 2024 (requires latest Gold Book). Compare to NYISO actuals.

- Satisfies Task 1.4 "tests for a selected class year" bullet extended to systematic form.

- Produces the multi-year validation table that will appear in every paper.

### End-of-phase deliverables (Months 1-2)

- v1-calibrated stochastic baseline reproducible.

- BESS real fleet per year.

- Queryable database with provenance.

- All known calibration issues addressed or explicitly documented.

- Systematic 6-year validation table.

## Months 3-4: NYCA inter-area flow and Digital Twin interface

Goal: consolidate Task 1.2's inter-area flow methodology and begin Task 1.4 / 1.5's Digital Twin work. Digital Twin interface is pulled forward here because downstream validation depends on it.

### Weeks 9-10: NYCA inter-area flow methodology

Write docs/nyca_flow_definition.md as a standalone deliverable covering the 7 internal interfaces with limits and physical meaning, the 4 external equivalents with the Path B cost methodology now implemented, and contingency-based limit derivation. Cross-check against NYISO's 2019-2024 Transmission Assessment Gold Book sections.

- Closes Task 1.2's "define NYCA inter-area flow" bullet cleanly.

### Weeks 11-12: Digital Twin output specification

Before you can interface with AGILe's Digital Twin, you need to know what output format it expects. Three tracks in parallel:

- Reach out to the AGILe team to obtain the Digital Twin data schema.

- Produce Vatic output in a schema-compatible format: hourly generator dispatch, storage dispatch, bus-level load.

- Document the mapping in docs/digital_twin_interface.md.

This serves the Task 1.5 "transfer key data elements" bullet, done now because the Digital Twin validation in Task 1.4 depends on the data pipe being operational.

### Weeks 13-16: First Digital Twin comparison

Run the pipeline for the NYISO class year selected by the AGILe team. Feed outputs to the Digital Twin. Compare. Iterate on discrepancies.

- Task 1.4 core deliverable.

- Expected outcome: initial comparison reveals discrepancies; iteration begins.

### Weeks 13-16 (parallel track): Per-bus LMP validation

Compare simulation per-bus LMPs to NYISO nodal LMPs. Quantify bus-level accuracy. Identifies whether the Kron-reduced network distorts locational prices beyond acceptable tolerance.

### End-of-phase deliverables (Months 3-4)

- NYCA inter-area flow fully documented.

- Digital Twin interface operational.

- First Digital Twin comparison report with diagnosed discrepancies.

- Per-bus LMP validation baseline.

## Months 5-6: Complete Task 1.3

Goal: pull together the weather, grid-scale solar, BTM solar, and test plan components that have been accumulating. Close Task 1.3 explicitly.

### Weeks 17-18: HRRR pipeline coverage extension

- Extend HRRR pipeline to cover all years 2018-2024 systematically.

- Resolve or document the early-2018 incomplete-horizon issue.

- Unified weather access: get_nyiso_weather(year, date_range) returning consistent actuals and forecasts for all plants.

### Weeks 19-20: Grid-scale solar integration

2019 model has only 2 solar sites. For 2022+ when NYISO has roughly 500 MW of grid-scale solar, integrate real plants.

- Update FleetUpdater to include solar from Gold Book and EIA-860.

- Regenerate 2022, 2023, 2024 baselines with real solar.

### Weeks 21-22: BTM solar integration

This is the Task 1.3 bullet that is fully not-started. Two approaches:

- Option A: Keep BTM absorbed in net load. Document as modeling choice.

- Option B: Separate BTM as explicit non-dispatchable generator at zone-representative buses, then add BTM to gross load. Uses NYISO btmactualforecast dataset.

Consult with PI on whether Option B is needed for Task 2.1's "large-scale" model before committing.

### Weeks 23-24: Systematic test plan

Document the test plan for Task 1.3's "develop and execute test plan" bullet. Specify: tests on every change, tests before every experiment, tests before publication.

- Deliverable: docs/test_plan.md

- Extends existing 21+2 regression suite with weather and BTM tests.

### End-of-phase deliverables (Months 5-6)

- Task 1.3 fully complete.

- Historic/actuals database across all years with explicit weather, grid-scale solar, and (if applicable) BTM solar.

- Test plan document.

## Months 7-8: First research experiment

Goal: produce the first publishable result. Prior months built infrastructure; this is what it is for.

The experiment: cost-of-uncertainty evolution across years 2019-2024 on a matched summer week. How does the operational value of stochastic commitment change as NYISO decarbonizes?

### Weeks 25-26: Experiment design and pilot

- Commit to the experiment scope.

- Run one year at 10 scenarios to calibrate compute and shake out residual issues.

- Confirm stochastic ensemble produces expected spread and no failures.

### Weeks 27-30: Full experimental campaign

- Run 100-scenario ensembles for the matched summer week in each of 2019-2024.

- Compute: roughly 6-8 hours per year per 100-scenario run; full campaign in 2-3 weeks with parallelization.

- Satisfies Task 1.2's "use MC engine to create a historical database" bullet.

### Weeks 31-32: Analysis and writeup

- Cross-year cost-of-uncertainty table with confidence intervals.

- LMP fan charts: 2019 vs 2024 side-by-side.

- Commitment heatmaps showing shifts in scenario-sensitive units.

- Decomposition: fuel prices vs. fleet composition vs. load growth as drivers.

- First paper draft outline.

### Kron validation (parallel track)

- Cross-check Kron-reduced network against full NPCC-140 on a single dispatch day.

- Quantify impedance and PTDF differences.

- Addresses the cross-cutting fidelity issue.

### End-of-phase deliverables (Months 7-8)

- Historical database of stochastic ensembles across years.

- First-draft paper on cost-of-uncertainty evolution.

- Kron reduction fidelity report.

## Months 9-11: Task 2.1 - large-scale stochastic model

Goal: extend PGscen-NYISO to the "large-scale" model specified in Task 2.1. What "large-scale" means should be confirmed with the PI early.

### Possible interpretations of 'large-scale'

- Add generator outage and forced-outage scenarios to the MC engine.

- Extend to full-year simulations instead of single weeks.

- Add transmission contingency scenarios.

- Incorporate CLCPA-target renewable projections for 2030.

Pick one or two based on what is most useful for Task 2.2's tradeoff analysis.

### Weeks 33-36: Scale the stochastic model

- Implement chosen extensions.

- Update PGscen scenario generation to cover new stochastic dimensions.

### Weeks 37-40: Validation

- Validate against observed outage statistics (for outages) or NYISO planning scenarios (for future-year projections).

### Weeks 41-44: Extended ensemble runs

- Run the large-scale model at higher coverage (full year, more scenarios, more years).

- Produces the database Task 2.2 will use for tuning.

### End-of-phase deliverables (Months 9-11)

- Task 2.1 complete.

- Large-scale stochastic model operational.

- Extended scenario database across years.

## Months 12-13: Task 2.2 - cost vs. environmental tradeoffs

Goal: add emissions accounting and produce tradeoff analysis. Directly answers Task 2.2.

### Weeks 45-48: Emissions accounting

- Add emissions to Vatic objective or as post-processing layer.

- RGGI carbon prices: $13/ton (2019) to $15/ton (2023) trajectory.

- SO2 and NOx rates by unit from EPA CAMD.

- Optional: methane leakage for gas units.

### Weeks 49-52: Tradeoff analysis

- Parameterized studies: vary carbon price, observe cost and emissions changes.

- Compare 2019 baseline, 2023 real-world, CLCPA target scenarios.

- Produce Pareto-style cost-vs-emissions curves for NYISO decarbonization.

### End-of-phase deliverables (Months 12-13)

- Task 2.2 complete.

- Tradeoff curves between cost and emissions across the decarbonization transition.

## Month 14: Task 1.5 completion and final report

Goal: close remaining Digital Twin work, write the user procedure, produce the final project report.

### Weeks 53-56: Digital Twin integration finalization

- Complete remaining iteration from Task 1.4 Digital Twin comparison.

- Ensure Market Emulator outputs transfer reliably to Digital Twin.

### Weeks 57-58: Final report

- Software documentation.

- User procedure for Market Emulator, use-case definition, and modification workflow.

- Software demonstration.

- Final Task 1.5 deliverable.

# 6. Why this ordering

## Foundation before research

Months 1-2 look unambitious but six major silent bugs were discovered during development (scalar compression, timezone mismatch, cold-start contamination, load scenarios never applied, deterministic day-by-day UC, SOC persistence). A research paper built on unconsolidated pipeline is a ticking citation-correction. Locking in the foundation makes everything downstream faster.

## Database and inter-area flow early

Task 1.2's harder bullets (database, inter-area flow methodology) unblock Task 1.4's Digital Twin comparison, which needs to be operational well before the 17-month horizon of Task 1.5.

## Task 1.3 before Task 2.1

Task 2.1 specifies "large-scale stochastic model from weather data." The large-scale model cannot be built until the weather pipeline is systematically complete (Task 1.3).

## Research experiment at mid-timeline

Months 7-8 are the earliest point with enough validated infrastructure to produce a publishable result. Running earlier risks another round of calibration gaps. Running later means no paper in year one, which hurts the research trajectory.

## Task 2.2 as capstone

Emissions vs. cost tradeoffs depend on every piece of infrastructure built. Putting it at the end means the full stack is available to answer the question cleanly.

## Task 1.5 absorbed into the structure

The 17-month horizon of Task 1.5 overlaps everything. Digital Twin interface work sits in Months 3-4 (when Task 1.4 needs it); documentation and final-report bullets sit at the end (when there is something to document).

# 7. Conversations to have with the PI early

Two questions shape the timeline and should be confirmed in Month 1 to avoid rework later.

## What does 'large-scale stochastic model' mean in Task 2.1?

- If "add contingencies" - about 2 months of work.

- If "full-year, full-state including BTM solar and CLCPA projections" - 4+ months.

The plan above assumes something in between (3 months). Narrowing the target improves accuracy of Months 9-11.

## What is the Digital Twin interface format?

- If AGILe's team has a schema ready, Months 3-4 proceed smoothly.

- If the schema is being designed, there is coupling risk and the conversation should start in Month 1.

# 8. Dependency map

Work items are ordered by dependency. The chart below shows what unblocks what.

| Work item | Depends on | Unblocks |
| --- | --- | --- |
| v1 stochastic pilot | BESS SOC fix (done) | Any multi-year ensemble work |
| BESS fleet updater | v1 pilot stable | Post-2022 realistic simulations |
| Database layer | Current file cache working | Provenance, easier audits |
| Path B import pricing | Research into Zone D LMP data | 2022 LMP improvement, Task 1.4 credibility |
| Multi-year validation sweep | All Months 1-6 work | Paper-ready validation table |
| NYCA flow doc | Path B imports | Task 1.2 closure |
| Digital Twin interface | AGILe schema available | Task 1.4 and 1.5 execution |
| Digital Twin comparison | Interface + NYCA flow | Task 1.4 completion |
| HRRR coverage extension | Existing PGscen pipeline | Task 1.3 and 2.1 |
| Grid-scale solar integration | Updated FleetUpdater | Task 1.3 and 2.1 accuracy |
| BTM solar integration | PI decision on scope | Task 2.1 scale |
| Cost-of-uncertainty experiment | Months 1-6 all complete | First paper |
| Large-scale stochastic model | Task 1.3 complete | Task 2.2 tradeoff analysis |
| Emissions accounting | Large-scale MC database | Task 2.2 completion |
| Final Digital Twin integration | Months 3-4 interface + iteration | Task 1.5 |
| Final report | Everything above | Project closure |

# 9. Risks and mitigations

## Silent bugs re-emerging

The development history shows silent bugs at every layer. Mitigation: the regression suite (21 fast + 2 slow tests with mutations) catches the six known bug classes. New bugs should trigger new regression tests before fixes are called complete.

## Digital Twin schema delayed

If AGILe cannot provide a Digital Twin schema in Month 1-2, Months 3-4 work slips. Mitigation: begin schema conversation in Month 1 even while doing foundation work. If delay occurs, fill with Task 1.3 work pulled forward.

## PGscen convergence edge cases

Gap #8 in the regression README notes PGscen can silently fail to converge. Mitigation: when running Months 7-8 experiment, monitor convergence logs and flag any date/asset combination that produces degenerate scenarios.

## Scope creep on Task 2.1 'large-scale'

Without PI confirmation on scope, Task 2.1 could balloon. Mitigation: Month 1 conversation with PI to pin scope.

## Publication pressure pulling research forward

Temptation to run the cost-of-uncertainty experiment before Months 1-6 foundation work is complete. Mitigation: foundation phases produce numbers that go into the paper's validation section. Rushing to the experiment means weaker validation and higher risk of needing corrections.

# 10. End-of-project deliverables checklist

By Month 14, these artifacts should exist:

- Reproducible v1-calibrated stochastic pipeline.

- Year-agnostic NyisoLoader with thermal and BESS fleet updaters across 2018-2024.

- Queryable database of NYISO, EIA, and simulation outputs with provenance.

- NYCA inter-area flow methodology document.

- Path B import pricing implementation.

- Full HRRR weather pipeline across all years.

- Grid-scale solar integration in FleetUpdater.

- BTM solar model (Option A or B per PI decision).

- Systematic test plan and regression suite (original 21+2 plus additions).

- Multi-year deterministic validation table (2019-2024).

- Kron reduction fidelity report.

- Digital Twin interface specification and implementation.

- Digital Twin comparison report with iteration history.

- Historical database of stochastic ensembles across years.

- First research paper draft (cost-of-uncertainty evolution).

- Large-scale stochastic model (scope per PI).

- Emissions accounting layer in Vatic.

- Cost-vs-emissions tradeoff analysis.

- Market Emulator user procedure document.

- Final project report with software demonstration.